## Ticket Audit
OPEN TICKETS - NO TASKS
Ticket No | Open Date | Owner | Total Activities | Category | Ticket Summary | Resolution | Resolution From
486494 | 2021-01-19 | Gedikli, Natalie | 3 |  | Need 8 custom SQL queries for annual California Core Quality Measures (CQM) reporting | ** Natalie actively working with development | Jake
481212 | 2020-07-30 | Malone, Kim | 1 | Account Mgt | 5 Year Renewal signed (expires 06/30/2025) Contract #1229586 | ** Open f/u to Kim Malone re tracking contract expirations. | Jake
479046 | 2020-05-18 | Pohanka, Jennifer | 368 | Account Mgt | Custom SQL Query: Request for CAD data | ** Perpetually open ticket for ongoing custom reporting. | Jake
478981 | 2020-05-14 | Nystrom, Jake | 15 |  | CAD RD or API Documentation | ** Open CAD RD or API Documentation request | Jake
476059 | 2020-02-21 | Nystrom, Jake | 18 | Account Mgt | Request for call from manager | ** Open f/u to Tom O. Request is to add fields from MT into AQB for reporting. NOTE: There is an open project to see if SFD would benefit form the HEMS 2.0 Xport, waiting for acceptance response from customer. | Jake
460253 | 2019-02-22 | Gedikli, Natalie | 49 | Account Mgt | Changes to billing process and billing agency user access. | HLMGR-732 deployed. Waiting on Billing vendor | Jake/Tom
488289 | 2021-03-15 | Gedikli, Natalie |  |  |  | ** Chief Marshall will provide updated list of Dispatch Codes from CAD. Will use HEMS setup table worksheet to upload new codes (Leslie will provide descriptions, service level, etc). Will also in-activate existing Dispatch codes once new ones ready to upload.
OPEN TICKETS - TASKS ASSIGNED
Ticket | Task | Status | Task Description
487928 | HLMT-4340 | MT 6.45 MR1 (RELEASED March 16th) | Event Log -> Vitals: Temporary Performance Error occurs when PowerFields are Assigned to items like Systolic, Diastolic (ect.)
487928 | HLMT-4332 | MT 6.46 Proposed | Event Log -> Vitals -> Add validation preventing DBP values 1-9
487242 | HLMT-4322 | MT 6.47 (June/July) | Patient -> Age: Add validation to conform to NEMSIS requirements
486685 | HLMGR-1871 | MGR 5.46 (April) | Parsing -> Use latitude/longitude for shortest distance calculation whenever possible and look at returned quality code
486685 | HLMGR-1736 | MGR 5.46 Proposed | Mapping -> ePCR/CAD Matching Updates
486483 | HLMGR-2312 | Ready To Release | eRecord -> Data Validator -> Unmatched Forms: 'You do not have rights to view the requested data' when viewing attachments
486375 | HLMT-4251 | MT On Deck (reviewed with Dev, more research is needed to identify resolution) | Rare issue with concurrent web requests
484139 | HLMGR-2103 | MGR 5.46 (April) | Dashboard -> ePCRs in MobileTouch: Not Possible/Not Likely validations are not displayed
482521 | HLMT-4223 | Dev Review (to be discussed in next Dev meeting) | Signatures Tab - Validations: When both Patient and Refusal signatures are required, completing one clears both validations
479129 | HLMT-3913 | MT 6.47 (June/July) | Sharing Call/Crew-> Call Times: Transfer of Care time displays overlay to receiving form
478201 | HLMGR-1161 | PowerFields Phase 2 | Reports -> Prehospital Care Report Summary / Billing Review: Determine sort order for Powerfields
478150 | HLMT-4162 | PowerFields Phase 2 | PowerFields: PowerField Group Description does not display if the first included PowerField contains multiple lines
478119 | HLMT-3971 | PowerFields Phase 2 | PowerFields: Always displays alphabetically in MT regardless of order in setup
476696 | HLMT-2042 | MobileTouch Issues Backlog | Issues entering / changing times that occurred during DST window (central) but not in DST window for other time zones |  |  |  | New Ticket # 488360
476104 | HLMGR-1534 | MGR 5.47 (June/July) | Setup -> Billing -> Medical History -> Add ability to define State Export Value
475631 | HLMT-4134 | Dev Review (to be discussed in next Dev meeting) | Event Log: Difficulty documenting numeric / Not Taken vitals with an associated PowerField
464637 | HLMGR-2392 | MGR 5.48 Proposed | Setup -> Application Settings -> MobileTouch Configs: Create config option to always require Med Wasted signatures, even if wasted amount is 0
460253 | HLMGR-732 | MGR 5.36 (RELEASED) | Xchange -> HealthEMS Export -> Prehospital Care Report -> Not including attachments
483586 | HLMT-4259 | MT On Deck (reviewed with Dev, more research is needed to identify resolution) | Signatures-> add MobileTouch config to manage Narcotics Wasted validations